## Dashboard
📊 Roadmap Progress Dashboard
Auto-updates as you change Status in the '3-Month Roadmap' tab.
Metric | Count
Total Study Days | 78
Days Done | 0
Days In Progress | 0
Days Not Started | 78
% Complete | 0%
High Priority Remaining | 60
Month 1 Days Done | 0
Month 2 Days Done | 0
Month 3 Days Done | 0
Weekly Themes Reference
Month | Week | Theme | Total Hours (approx.) | Focus Area
1 | 1 | SQL Mastery + Azure Cloud Fundamentals | ~15-18 hrs | Foundations (SQL/Python/Azure Basics)
1 | 2 | Python for Data Engineering | ~15-18 hrs | Foundations (SQL/Python/Azure Basics)
1 | 3 | Azure Storage, ADLS Gen2 & Data Modeling | ~15-18 hrs | Foundations (SQL/Python/Azure Basics)
1 | 4 | Azure Data Factory (ADF) Deep Dive | ~15-18 hrs | Foundations (SQL/Python/Azure Basics)
2 | 5 | Azure Databricks & Delta Lake | ~15-18 hrs | Core Azure + AI/ML Crossover
2 | 6 | Azure Synapse Analytics & Azure SQL | ~15-18 hrs | Core Azure + AI/ML Crossover
2 | 7 | AI/ML Fundamentals for Data Engineers | ~15-18 hrs | Core Azure + AI/ML Crossover
2 | 8 | Azure AI Services, Azure ML & Modern AI Data Patterns | ~15-18 hrs | Core Azure + AI/ML Crossover
3 | 9 | System Design for Data Pipelines - Part 1 | ~15-18 hrs | System Design + Interview Sprint
3 | 10 | System Design Part 2 + Big 4 / Enterprise Patterns | ~15-18 hrs | System Design + Interview Sprint
3 | 11 | Mock Interviews & Weak-Area Sprint | ~15-18 hrs | System Design + Interview Sprint
3 | 12 | Resume Polish, Targeted Applications & Mock Round 2 | ~15-18 hrs | System Design + Interview Sprint
3 | 13 | Final Interview Sprint & Buffer Week | ~15-18 hrs | System Design + Interview Sprint

## 3-Month Roadmap
🗺️ 3-Month Azure Data Engineer + AI Roadmap (Beginner → Interview-Ready)
Day-by-day plan · Mon-Fri: 2-3 hrs new content · Saturday: revision + hands-on project · Sunday: rest
Month | Week | Day | Date | Main Topic | Sub-Concepts (Detailed) | Resource Type | Resource Name + Link | Est. Time | Status | Priority | Notes
MONTH 1 · WEEK 1 — SQL Mastery + Azure Cloud Fundamentals
1 | 1 | Mon | 2026-06-22 | SQL Foundations Refresher | SELECT/WHERE/GROUP BY/HAVING; JOINS (INNER/LEFT/RIGHT/FULL/SELF) with multi-table examples; set theory behind joins | YouTube | Luke Barousse - SQL for Data Analytics (free) https://youtube.com/@LukeBarousse | 2.5 hrs | Not Started | High | Practice every join type by hand before running queries
1 | 1 | Tue | 2026-06-23 | SQL Window Functions | ROW_NUMBER, RANK, DENSE_RANK, NTILE; LAG/LEAD; PARTITION BY logic; running totals & moving averages | Course | Mode Analytics SQL Tutorial - Window Functions https://mode.com/sql-tutorial/sql-window-functions/ | 2.5 hrs | Not Started | High | Window functions are the #1 SQL interview filter at Big 4/MAANG
1 | 1 | Wed | 2026-06-24 | SQL Advanced - CTEs & Subqueries | Recursive CTEs; correlated vs non-correlated subqueries; EXISTS vs IN vs JOIN performance tradeoffs | Doc | Microsoft Learn - Use CTEs in T-SQL https://learn.microsoft.com/en-us/sql/t-sql/queries/with-common-table-expression-transact-sql | 2.5 hrs | Not Started | High | Recursive CTEs commonly asked for org-hierarchy problems
1 | 1 | Thu | 2026-06-25 | SQL Query Optimization | Execution plans; indexing strategy (clustered vs non-clustered); query rewriting for performance; partitioning basics | YouTube | Decoded by Suraj - SQL Query Optimization https://youtube.com/@decodedbysuraj | 2.5 hrs | Not Started | Medium | Be ready to explain how you optimized a slow query in past projects
1 | 1 | Fri | 2026-06-26 | Azure Fundamentals (AZ-900 core) | Azure global infra (regions/AZs); core services map; Azure Resource Manager; subscriptions/resource groups; IAM basics (RBAC) | Course | Microsoft Learn - AZ-900 Path https://learn.microsoft.com/en-us/training/paths/microsoft-azure-fundamentals-describe-cloud-concepts/ | 2.5 hrs | Not Started | Medium | Skip if already AZ-900 certified; skim for gaps only
1 | 1 | Sat | 2026-06-27 | Revision + Hands-on: SQL Practice Lab | Solve 15 SQL problems (joins, window fns, CTEs) on a practice DB; document 3 tricky queries with explanation | Doc | StrataScratch / LeetCode Database (free tier) https://leetcode.com/studyplan/sql/ | 3 hrs | Not Started | High | Maintain a personal 'SQL patterns' notes doc - reuse this in mock interviews
MONTH 1 · WEEK 2 — Python for Data Engineering
1 | 2 | Mon | 2026-06-29 | Python Core Refresher | Data structures (list/dict/set/tuple) performance; comprehensions; *args/**kwargs; generators & iterators | YouTube | Corey Schafer - Python Intermediate Series https://youtube.com/@coreyms | 2.5 hrs | Not Started | Medium | Skip basics if confident; focus on generators (used heavily in ETL)
1 | 2 | Tue | 2026-06-30 | Pandas for ETL | DataFrame ops (merge/groupby/pivot/melt); handling nulls & dtypes; vectorization vs apply() performance; chunked reading for large files | Course | Kaggle - Pandas Micro-course (free) https://www.kaggle.com/learn/pandas | 3 hrs | Not Started | High | Practice on a 1M+ row CSV to feel real performance differences
1 | 2 | Wed | 2026-07-01 | PySpark Fundamentals I | Spark architecture (driver/executor/cluster manager); RDD vs DataFrame vs Dataset; lazy evaluation; transformations vs actions | YouTube | Afaque Ahmad - PySpark Tutorial Series https://youtube.com/@AfaqueAhmad | 3 hrs | Not Started | High | Core for Databricks interviews - understand WHY lazy eval matters
1 | 2 | Thu | 2026-07-02 | PySpark Fundamentals II | DataFrame API deep dive (select/filter/withColumn/groupBy/agg); UDFs vs built-in functions; broadcast variables; partitioning & shuffling | Doc | Apache Spark Official Docs - DataFrame Guide https://spark.apache.org/docs/latest/sql-getting-started.html | 3 hrs | Not Started | High | Shuffling is a top system-design discussion point - know how to minimize it
1 | 2 | Fri | 2026-07-03 | Python + Error Handling + Logging for Pipelines | try/except patterns for ETL; custom exceptions; structured logging; retry logic with exponential backoff; config management (YAML/env vars) | Doc | Real Python - Logging Best Practices https://realpython.com/python-logging/ | 2.5 hrs | Not Started | Medium | Production-grade error handling is a strong differentiator in interviews
1 | 2 | Sat | 2026-07-04 | Revision + Hands-on: Mini ETL Script | Build a Python script: read CSV -> clean with Pandas -> transform -> write Parquet; add logging + error handling | Doc | Personal project - use sample Kaggle dataset https://www.kaggle.com/datasets | 3 hrs | Not Started | High | Push this to GitHub - first portfolio artifact
MONTH 1 · WEEK 3 — Azure Storage, ADLS Gen2 & Data Modeling
1 | 3 | Mon | 2026-07-06 | Azure Storage Fundamentals | Storage account types; Blob vs File vs Queue vs Table storage; access tiers (Hot/Cool/Archive); replication (LRS/ZRS/GRS) | Doc | Microsoft Learn - Azure Storage Overview https://learn.microsoft.com/en-us/azure/storage/common/storage-introduction | 2 hrs | Not Started | Medium | Know cost implications of each tier - common interview question
1 | 3 | Tue | 2026-07-07 | ADLS Gen2 Deep Dive | Hierarchical namespace vs flat; folder structure best practices (bronze/silver/gold); ACLs vs RBAC; mounting in Databricks | YouTube | WafaStudies - ADLS Gen2 Complete Tutorial https://youtube.com/@WafaStudies | 2.5 hrs | Not Started | High | Bronze/Silver/Gold (medallion architecture) appears in almost every Azure DE interview
1 | 3 | Wed | 2026-07-08 | Data Modeling Fundamentals | OLTP vs OLAP; normalization (1NF-3NF) vs denormalization tradeoffs; star schema vs snowflake schema; fact & dimension tables | Course | Coursera/YouTube - Kimball Data Warehouse Toolkit concepts https://www.kimballgroup.com/ | 2.5 hrs | Not Started | High | Be ready to design a star schema live on a whiteboard
1 | 3 | Thu | 2026-07-09 | Data Modeling - Slowly Changing Dimensions | SCD Type 0/1/2/3 with real examples; surrogate keys vs natural keys; handling late-arriving facts | Doc | Microsoft Learn - Dimensional modeling https://learn.microsoft.com/en-us/power-bi/guidance/star-schema | 2.5 hrs | Not Started | High | SCD Type 2 implementation is a very common take-home/interview ask
1 | 3 | Fri | 2026-07-10 | Data Warehousing Concepts | Data warehouse vs data lake vs lakehouse; ETL vs ELT; staging layers; data partitioning strategies for warehouses | YouTube | Seattle Data Guy - Data Warehouse Concepts https://youtube.com/@SeattleDataGuy | 2.5 hrs | Not Started | High | Lakehouse concept ties directly into Databricks/Delta Lake next week
1 | 3 | Sat | 2026-07-11 | Revision + Hands-on: Design a Star Schema | Design a star schema for an e-commerce dataset (fact_orders, dim_customer, dim_product, dim_date); document SCD strategy | Doc | Self-driven exercise - use draw.io or Lucidchart free tier | 3 hrs | Not Started | High | Save diagram - reuse in portfolio/resume discussions
MONTH 1 · WEEK 4 — Azure Data Factory (ADF) Deep Dive
1 | 4 | Mon | 2026-07-13 | ADF Architecture & Core Components | Pipelines, activities, datasets, linked services; Integration Runtime (Azure/Self-hosted/SSIS); triggers (schedule/tumbling window/event) | Doc | Microsoft Learn - ADF Introduction https://learn.microsoft.com/en-us/azure/data-factory/introduction | 2.5 hrs | Not Started | High | Integration Runtime choice is a frequent scenario-based question
1 | 4 | Tue | 2026-07-14 | ADF Copy Activity & Data Flows | Copy activity performance tuning (DIU, parallel copy); Mapping Data Flows vs Wrangling Data Flows; schema drift handling | YouTube | WafaStudies - ADF Data Flows Tutorial https://youtube.com/@WafaStudies | 3 hrs | Not Started | High | Hands-on: build one Mapping Data Flow with a join + aggregate transform
1 | 4 | Wed | 2026-07-15 | ADF Control Flow & Parameterization | ForEach, If, Switch, Until activities; pipeline parameters vs variables; dynamic content expressions; parameterized linked services for reusability | Course | Udemy - Azure Data Factory (search 'ADF Mastery' - check current sales) https://www.udemy.com/topic/azure-data-factory/ | 2.5 hrs | Not Started | High | Dynamic/parameterized pipelines = sign of senior-level ADF maturity
1 | 4 | Thu | 2026-07-16 | ADF Monitoring, CI/CD & Error Handling | Pipeline monitoring & alerts; retry policies; Try-Catch pattern using activity dependencies; ADF + Azure DevOps CI/CD (ARM templates/Git integration) | Doc | Microsoft Learn - CI/CD in ADF https://learn.microsoft.com/en-us/azure/data-factory/continuous-integration-delivery | 2.5 hrs | Not Started | Medium | CI/CD knowledge separates mid from senior candidates
1 | 4 | Fri | 2026-07-17 | ADF Integration with Other Services | ADF -> Databricks notebook activity; ADF -> Synapse pipelines; Key Vault integration for secrets; metadata-driven pipeline design pattern | YouTube | Adam Marczak - Azure for Everyone (ADF integrations) https://youtube.com/@AdamMarczakAzure | 2.5 hrs | Not Started | High | Metadata-driven pipelines = a top system-design talking point
1 | 4 | Sat | 2026-07-18 | Revision + Hands-on: Build End-to-End ADF Pipeline | Build pipeline: ingest CSV from Blob -> transform via Data Flow -> load to ADLS Gen2 (bronze/silver); add a failure-handling branch | Doc | Azure Free Tier account (12-month free + $200 credit) https://azure.microsoft.com/free/ | 3.5 hrs | Not Started | High | Screenshot pipeline + document design decisions for portfolio/resume
MONTH 2 · WEEK 5 — Azure Databricks & Delta Lake
2 | 5 | Mon | 2026-07-20 | Databricks Platform Fundamentals | Workspace, clusters (all-purpose vs job clusters), notebooks; cluster sizing & autoscaling; Databricks Runtime versions | Doc | Microsoft Learn - Azure Databricks Overview https://learn.microsoft.com/en-us/azure/databricks/introduction/ | 2.5 hrs | Not Started | High | Understand cost implications of cluster choices - frequently asked
2 | 5 | Tue | 2026-07-21 | Delta Lake Fundamentals | ACID transactions on data lakes; transaction log (_delta_log); time travel; schema enforcement & evolution | YouTube | Databricks Official - Delta Lake Fundamentals https://youtube.com/@Databricks | 2.5 hrs | Not Started | High | Delta Lake is THE differentiator topic for Azure DE roles in 2026
2 | 5 | Wed | 2026-07-22 | Delta Lake Operations | MERGE/UPSERT patterns; OPTIMIZE & Z-ORDER; VACUUM command & retention; CDC (Change Data Capture) with Delta | Doc | Delta Lake Official Docs https://docs.delta.io/latest/delta-batch.html | 3 hrs | Not Started | High | MERGE for SCD Type 2 implementation - practice this exact pattern
2 | 5 | Thu | 2026-07-23 | Databricks Medallion Architecture | Bronze/Silver/Gold layer design in Databricks; Auto Loader for incremental ingestion; Delta Live Tables (DLT) overview | YouTube | WafaStudies - Databricks Medallion Architecture https://youtube.com/@WafaStudies | 2.5 hrs | Not Started | High | Be ready to design a full medallion pipeline on a whiteboard
2 | 5 | Fri | 2026-07-24 | Databricks Performance & Unity Catalog | Partition pruning; caching strategies; Photon engine basics; Unity Catalog for governance (data lineage, access control) | Doc | Microsoft Learn - Unity Catalog https://learn.microsoft.com/en-us/azure/databricks/data-governance/unity-catalog/ | 2.5 hrs | Not Started | Medium | Unity Catalog is increasingly asked at senior-level interviews in 2026
2 | 5 | Sat | 2026-07-25 | Revision + Hands-on: Build Medallion Pipeline in Databricks | Bronze (raw ingest) -> Silver (cleaned/deduped via MERGE) -> Gold (aggregated business tables); use Databricks Community Edition or Azure trial | Doc | Databricks Community Edition (free) https://community.cloud.databricks.com/ | 3.5 hrs | Not Started | High | Strong portfolio piece - document with notebook + architecture diagram
MONTH 2 · WEEK 6 — Azure Synapse Analytics & Azure SQL
2 | 6 | Mon | 2026-07-27 | Synapse Analytics Architecture | Synapse workspace components; Dedicated SQL Pool vs Serverless SQL Pool vs Spark Pool; when to use which | Doc | Microsoft Learn - Synapse Analytics Overview https://learn.microsoft.com/en-us/azure/synapse-analytics/overview-what-is | 2.5 hrs | Not Started | High | Pool selection scenario questions are very common
2 | 6 | Tue | 2026-07-28 | Dedicated SQL Pool Deep Dive | Distribution strategies (hash/round-robin/replicated); table design for MPP; CTAS for performance; workload management (resource classes) | YouTube | WafaStudies - Synapse Dedicated SQL Pool https://youtube.com/@WafaStudies | 3 hrs | Not Started | High | Distribution strategy choice is a classic system-design interview question
2 | 6 | Wed | 2026-07-29 | Synapse Pipelines & Spark Pools | Synapse Pipelines vs ADF (when to use which); Spark Pool notebooks; integration with Power BI for serving layer | Doc | Microsoft Learn - Synapse Pipelines https://learn.microsoft.com/en-us/azure/synapse-analytics/pipeline/ | 2.5 hrs | Not Started | Medium | Many orgs use Synapse Pipelines instead of standalone ADF - know overlap
2 | 6 | Thu | 2026-07-30 | Azure SQL Database Fundamentals | DTU vs vCore purchasing models; elastic pools; backup/restore & point-in-time recovery; indexing in Azure SQL specifically | Doc | Microsoft Learn - Azure SQL Database Overview https://learn.microsoft.com/en-us/azure/azure-sql/database/sql-database-paas-overview | 2 hrs | Not Started | Medium | Know the difference vs SQL Managed Instance vs SQL on VM
2 | 6 | Fri | 2026-07-31 | Performance Tuning Across Azure SQL/Synapse | Query Store; missing index recommendations; statistics & cardinality estimation; partitioned tables and columnstore indexes | YouTube | Azure SQL Tips - Performance Tuning Series https://youtube.com/results?search_query=azure+sql+performance+tuning | 2.5 hrs | Not Started | Medium | Columnstore index knowledge signals warehouse-level expertise
2 | 6 | Sat | 2026-08-01 | Revision + Hands-on: Synapse Mini Project | Load sample data into Dedicated SQL Pool; design distribution strategy; write 5 analytical queries with CTAS optimization | Doc | Azure free trial Synapse workspace https://azure.microsoft.com/free/ | 3 hrs | Not Started | High | Document your distribution strategy reasoning - great interview talking point
MONTH 2 · WEEK 7 — AI/ML Fundamentals for Data Engineers
2 | 7 | Mon | 2026-08-03 | ML Fundamentals - Core Concepts | Supervised vs unsupervised vs reinforcement learning; train/validation/test splits; overfitting/underfitting; bias-variance tradeoff | Course | Google - Machine Learning Crash Course (free) https://developers.google.com/machine-learning/crash-course | 2.5 hrs | Not Started | High | You don't need to build models - you need to speak the language fluently
2 | 7 | Tue | 2026-08-04 | ML Fundamentals - Algorithms Overview | Linear/logistic regression intuition; decision trees & random forests; basics of neural networks (no deep math needed); evaluation metrics (accuracy, precision/recall, RMSE, AUC) | YouTube | StatQuest with Josh Starmer https://youtube.com/@statquest | 2.5 hrs | Not Started | High | StatQuest explains intuition without heavy math - ideal for DE-level understanding
2 | 7 | Wed | 2026-08-05 | Feature Engineering & Feature Stores | Feature engineering basics (encoding, scaling, binning); what a feature store is and why it exists; Azure ML Feature Store / Databricks Feature Store concepts; online vs offline feature serving | Doc | Microsoft Learn - Azure Machine Learning Feature Store https://learn.microsoft.com/en-us/azure/machine-learning/concept-what-is-managed-feature-store | 3 hrs | Not Started | High | This is THE bridge topic between DE and AI roles - expect direct interview questions here
2 | 7 | Thu | 2026-08-06 | ML Data Pipelines & Data Quality for ML | Data pipelines feeding ML training vs inference; data drift & model drift; data validation (schema checks, anomaly detection); labeling pipelines overview | YouTube | Made With ML - MLOps fundamentals (free) https://madewithml.com/ | 2.5 hrs | Not Started | High | Data quality for ML is a growing, high-value DE specialization
2 | 7 | Fri | 2026-08-07 | MLOps Fundamentals | ML lifecycle (data -> train -> deploy -> monitor); model registry concept; CI/CD for ML (CI/CD/CT); monitoring model performance in production | Doc | Microsoft Learn - MLOps with Azure Machine Learning https://learn.microsoft.com/en-us/azure/machine-learning/concept-model-management-and-deployment | 2.5 hrs | Not Started | High | Know how a DE supports each MLOps stage - this is the AI/DE crossover story for interviews
2 | 7 | Sat | 2026-08-08 | Revision + Hands-on: Feature Pipeline Mini Project | Build a small feature engineering pipeline in PySpark/Pandas (raw data -> engineered features -> save to a 'feature table'); document drift-monitoring approach | Doc | Use a public dataset (e.g. Kaggle Titanic/House Prices) https://www.kaggle.com/datasets | 3 hrs | Not Started | High | This single project gives you a concrete AI+DE story for interviews
MONTH 2 · WEEK 8 — Azure AI Services, Azure ML & Modern AI Data Patterns
2 | 8 | Mon | 2026-08-10 | Azure Machine Learning Service | Azure ML workspace; compute instances/clusters; ML pipelines in Azure ML; model registry & endpoints (real-time vs batch) | Doc | Microsoft Learn - Azure Machine Learning https://learn.microsoft.com/en-us/azure/machine-learning/overview-what-is-azure-machine-learning | 2.5 hrs | Not Started | Medium | Know the platform at a conceptual level - deep hands-on ML is not your job as a DE
2 | 8 | Tue | 2026-08-11 | Azure AI/Cognitive Services Overview | Azure AI Search (formerly Cognitive Search); Form Recognizer/Document Intelligence; Azure OpenAI Service basics; how DEs build data pipelines feeding these services | Doc | Microsoft Learn - Azure AI Services https://learn.microsoft.com/en-us/azure/ai-services/what-are-ai-services | 2.5 hrs | Not Started | Medium | Azure OpenAI Service knowledge is increasingly expected in 2026 JDs
2 | 8 | Wed | 2026-08-12 | Vector Databases & RAG Pipelines (Conceptual) | What embeddings are; vector search basics; Retrieval-Augmented Generation (RAG) architecture; role of DE in building RAG data pipelines (chunking, embedding generation, indexing) | YouTube | IBM Technology - RAG Explained https://youtube.com/@IBMTechnology | 2.5 hrs | Not Started | High | RAG pipeline questions are now common even in 'traditional' DE interviews in 2026
2 | 8 | Thu | 2026-08-13 | Streaming Data Fundamentals | Batch vs streaming paradigms; Azure Event Hubs basics; Azure Stream Analytics overview; windowing concepts (tumbling/hopping/sliding) for streaming aggregation | Doc | Microsoft Learn - Azure Event Hubs https://learn.microsoft.com/en-us/azure/event-hubs/event-hubs-about | 2.5 hrs | Not Started | Medium | Streaming is often a 'bonus' topic but signals well-rounded DE skill
2 | 8 | Fri | 2026-08-14 | Real-Time + AI Integration Patterns | Lambda vs Kappa architecture; real-time feature serving for ML; Structured Streaming with Delta Lake (Spark) | YouTube | Databricks Official - Structured Streaming + Delta Live Tables https://youtube.com/@Databricks | 2.5 hrs | Not Started | Medium | Combines streaming + Delta Lake + ML serving - high-signal topic for senior roles
2 | 8 | Sat | 2026-08-15 | Revision + Hands-on: Month 2 Consolidation Project | Design (on paper/diagram) a full pipeline: ingestion (ADF) -> Databricks medallion -> feature table -> mock 'model serving' endpoint; write a 1-page architecture doc | Doc | Self-driven - use draw.io / Lucidchart | 3.5 hrs | Not Started | High | This becomes your primary 'tell me about a project' interview answer
MONTH 3 · WEEK 9 — System Design for Data Pipelines - Part 1
3 | 9 | Mon | 2026-08-17 | System Design Fundamentals for Data Engineers | How to approach a system design interview (clarify requirements -> high-level design -> deep dive -> tradeoffs); throughput/latency/consistency basics | YouTube | Exponent - Data Engineering System Design https://youtube.com/@tryexponent | 2.5 hrs | Not Started | High | Practice the structured approach - interviewers grade process, not just final answer
3 | 9 | Tue | 2026-08-18 | Designing Batch ETL Systems | Designing a pipeline for a large-scale batch ETL (e.g. 'design a system to process daily retail transactions'); idempotency; checkpointing; backfill strategy | Doc | Seattle Data Guy - System Design for Data Engineers (blog/YouTube) https://www.theseattledataguy.com/ | 3 hrs | Not Started | High | Idempotency is a must-mention keyword in almost every design answer
3 | 9 | Wed | 2026-08-19 | Designing Streaming Systems | Design a real-time analytics pipeline (e.g. 'design a system to track live user clickstream'); exactly-once vs at-least-once processing; handling late/out-of-order data | YouTube | ByteByteGo - System Design Streaming https://youtube.com/@ByteByteGo | 3 hrs | Not Started | High | ByteByteGo's visual explanations are excellent for retention
3 | 9 | Thu | 2026-08-20 | Designing for Scale - Partitioning & Sharding | Data partitioning strategies at scale; sharding key selection; handling data skew; hot partition problems and mitigation | Doc | Microsoft Learn - Data partitioning guidance https://learn.microsoft.com/en-us/azure/architecture/best-practices/data-partitioning | 2.5 hrs | Not Started | High | Data skew mitigation is a favorite deep-dive follow-up question
3 | 9 | Fri | 2026-08-21 | Designing for Reliability | Fault tolerance patterns; dead-letter queues; data quality gates (schema validation, anomaly checks); disaster recovery & RTO/RPO concepts | Doc | Microsoft Learn - Reliability patterns https://learn.microsoft.com/en-us/azure/architecture/framework/resiliency/ | 2.5 hrs | Not Started | Medium | RTO/RPO terms signal enterprise-grade thinking - use them precisely
3 | 9 | Sat | 2026-08-22 | Revision + Hands-on: Mock System Design Write-up | Pick 1 prompt ('design a pipeline for ride-hailing trip data') and write a full design doc: requirements, architecture diagram, tradeoffs, scaling plan | Doc | Self-driven - use ByteByteGo prompt library as reference | 3.5 hrs | Not Started | High | Time yourself to 45 min - matches real interview constraints
MONTH 3 · WEEK 10 — System Design Part 2 + Big 4 / Enterprise Patterns
3 | 10 | Mon | 2026-08-24 | Designing a Modern Data Platform (End-to-End) | Full platform design: ingestion -> lake -> warehouse -> serving -> BI/ML consumption; governance & security layer; cost-optimization considerations | YouTube | Andreas Kretz (Learn Data Engineering) - Platform Design https://youtube.com/@andreaskayy | 3 hrs | Not Started | High | Andreas Kretz's content is highly respected for real-world DE platform design
3 | 10 | Tue | 2026-08-25 | Data Governance & Security at Scale | Data masking & encryption (at-rest/in-transit); Azure Purview/Microsoft Purview for catalog & lineage; GDPR/compliance basics relevant to DE; column-level/row-level security | Doc | Microsoft Learn - Microsoft Purview https://learn.microsoft.com/en-us/purview/purview | 2.5 hrs | Not Started | High | Big 4 firms (Deloitte/EY/PwC/KPMG) heavily emphasize governance & compliance
3 | 10 | Wed | 2026-08-26 | Cost Optimization in Azure Data Platforms | Reserved instances vs pay-as-you-go; auto-pause for Synapse/Databricks clusters; storage tiering for cost; monitoring cost via Azure Cost Management | Doc | Microsoft Learn - Azure Cost Management https://learn.microsoft.com/en-us/azure/cost-management-billing/costs/overview-cost-management | 2 hrs | Not Started | Medium | Big 4 clients care deeply about cloud cost - mention this proactively
3 | 10 | Thu | 2026-08-27 | Consulting-Style Case Interview Prep (Big 4 specific) | How Big 4 frames DE problems as client case studies; structuring an answer using business-impact framing; communicating technical tradeoffs to non-technical stakeholders | YouTube | Search current 'Big 4 technology case interview' prep videos on YouTube | 2.5 hrs | Not Started | High | Big 4 interviews often blend technical + consulting communication style - practice both
3 | 10 | Fri | 2026-08-28 | Behavioral + Project Storytelling Prep | STAR method for behavioral questions; crafting a 2-minute 'tell me about a challenging pipeline' story; quantifying impact (data volume, cost saved, time saved) | Doc | Use your own past projects + Week 5/8 hands-on projects as source material | 2 hrs | Not Started | High | Prepare 4-5 STAR stories covering: conflict, failure, leadership, technical depth, ambiguity
3 | 10 | Sat | 2026-08-29 | Revision + Hands-on: Full Mock Interview (Self-recorded) | Record yourself answering 3 system design + 2 behavioral questions; review recording for clarity, structure, filler words | Doc | Self-driven; optionally use Pramp/Interviewing.io free mock slots https://www.pramp.com/ | 3.5 hrs | Not Started | High | Reviewing your own recording is uncomfortable but extremely high-ROI
MONTH 3 · WEEK 11 — Mock Interviews & Weak-Area Sprint
3 | 11 | Mon | 2026-08-31 | SQL + PySpark Rapid Review | Timed practice: 5 SQL problems (window fns/CTEs) + 3 PySpark transformation problems under 45 min total | Doc | StrataScratch + Databricks Community Edition https://www.stratascratch.com/ | 2.5 hrs | Not Started | High | Simulate real timed-assessment conditions (common at AWS/Google OA stage)
3 | 11 | Tue | 2026-09-01 | ADF + Databricks Scenario Drills | Answer 8-10 scenario questions out loud: 'how would you handle schema drift', 'how would you design incremental load', 'how would you debug a failed pipeline' | Doc | Compile questions from Weeks 4 & 5 notes + search 'Azure Data Engineer interview questions 2026' | 2.5 hrs | Not Started | High | Speaking answers out loud (not just reading) builds real interview fluency
3 | 11 | Wed | 2026-09-02 | Synapse + Data Modeling Scenario Drills | Practice explaining: distribution strategy choice, SCD Type 2 implementation, star schema design for a new business case (live whiteboard style) | Doc | Use Week 3 & 6 notes; practice on physical whiteboard or draw.io | 2.5 hrs | Not Started | High | Whiteboarding speed matters - practice drawing schemas quickly
3 | 11 | Thu | 2026-09-03 | AI/ML + MLOps Scenario Drills | Practice explaining: feature store role, data drift detection approach, how you'd support an ML team's data needs, RAG pipeline data flow | Doc | Use Week 7 & 8 notes | 2.5 hrs | Not Started | High | This is your differentiation area vs typical DE candidates - polish it
3 | 11 | Fri | 2026-09-04 | Live Mock Interview #1 (Technical) | Full 45-60 min mock: 1 SQL/coding round + 1 system design round; get feedback from a peer/mentor or use AI-assisted mock (e.g. ChatGPT/Claude as interviewer) | Doc | Pramp (free peer mock interviews) https://www.pramp.com/ or interviewing.io | 2 hrs | Not Started | High | Book this in advance - don't let it slip to 'someday'
3 | 11 | Sat | 2026-09-05 | Gap Analysis + Targeted Revision | Review mock interview feedback; identify top 3 weak areas; spend the day deep-diving ONLY those topics with fresh practice problems | Doc | Self-driven based on personal gap list | 3.5 hrs | Not Started | High | Be honest in gap analysis - this is the highest-leverage day of the week
MONTH 3 · WEEK 12 — Resume Polish, Targeted Applications & Mock Round 2
3 | 12 | Mon | 2026-09-07 | Resume Optimization for Azure DE + AI Roles | Quantify achievements (data volume, latency improvement, cost reduction); keyword-align to JD (ATS optimization); craft 1-2 project bullets highlighting AI/ML crossover | Doc | Use Job Tracker (Task 1) + target JDs for keyword matching | 2.5 hrs | Not Started | High | Tailor 2-3 resume versions for different role flavors (pure DE vs DE+AI heavy)
3 | 12 | Tue | 2026-09-08 | LinkedIn + Portfolio Polish | Update LinkedIn headline/about for Azure DE + AI positioning; publish 1 portfolio write-up (e.g. medallion architecture project from Week 5) | Doc | LinkedIn + GitHub README best practices (search current guides) | 2 hrs | Not Started | Medium | A polished GitHub README for your Week 5/8 project adds real credibility
3 | 12 | Wed | 2026-09-09 | Targeted Applications Sprint | Apply to 8-10 roles using the Job Tracker (Task 1); prioritize referrals where possible; customize cover note per company tier | Doc | Use Task 3 target company list | 2.5 hrs | Not Started | High | Quality + referral > quantity of blind applications
3 | 12 | Thu | 2026-09-10 | Advanced System Design Drill | Tackle 1 hard system design prompt end-to-end ('design a near-real-time fraud detection data pipeline') combining streaming + ML serving + governance | YouTube | ByteByteGo / Exponent advanced prompts https://youtube.com/@ByteByteGo | 2.5 hrs | Not Started | High | This combines almost every topic from the 3 months - good integration test
3 | 12 | Fri | 2026-09-11 | Live Mock Interview #2 (Behavioral + System Design) | Full mock focused on behavioral STAR stories + 1 system design question; request specific feedback on communication clarity | Doc | Pramp / interviewing.io / mentor network | 2 hrs | Not Started | High | Compare progress against Mock #1 - track improvement explicitly
3 | 12 | Sat | 2026-09-12 | Revision + Hands-on: Final Project Polish | Finalize and document your best end-to-end project (ADF + Databricks + Synapse + feature table); ensure GitHub repo + README are interview-ready | Doc | Consolidate Week 4/5/8 hands-on work | 3.5 hrs | Not Started | High | This project should be ready to screen-share in any interview within 2 minutes
MONTH 3 · WEEK 13 — Final Interview Sprint & Buffer Week
3 | 13 | Mon | 2026-09-14 | Full-Spectrum Rapid Review - Week 1 | Flash-review SQL window functions, CTEs, query optimization, Python/PySpark fundamentals using your own notes only (no new material) | Doc | Personal notes from Weeks 1-2 | 2 hrs | Not Started | High | Active recall: explain each topic out loud without looking at notes first
3 | 13 | Tue | 2026-09-15 | Full-Spectrum Rapid Review - Azure Core Services | Flash-review ADLS Gen2, ADF, Databricks/Delta Lake, Synapse - architecture diagrams from memory | Doc | Personal notes from Weeks 3-6 | 2 hrs | Not Started | High | Redraw each architecture diagram from memory, then check against notes
3 | 13 | Wed | 2026-09-16 | Full-Spectrum Rapid Review - AI/ML + MLOps | Flash-review feature stores, MLOps lifecycle, RAG pipelines, streaming + ML serving patterns | Doc | Personal notes from Weeks 7-8 | 2 hrs | Not Started | High | Practice your 'AI/DE crossover' pitch one more time - this is your edge
3 | 13 | Thu | 2026-09-17 | Full-Spectrum Rapid Review - System Design + Governance | Flash-review batch/streaming design patterns, partitioning/sharding, governance & cost optimization, Big 4 case-style framing | Doc | Personal notes from Weeks 9-10 | 2 hrs | Not Started | High | Re-run your timed 45-min design doc exercise from Week 9 Saturday
3 | 13 | Fri | 2026-09-18 | Live Mock Interview #3 (Full Loop Simulation) | Simulate a full interview loop if possible: 1 technical SQL/coding + 1 system design + 1 behavioral, back-to-back | Doc | Pramp / interviewing.io / mentor / senior colleague | 2.5 hrs | Not Started | High | This is your dress rehearsal - treat it as the real thing
3 | 13 | Sat | 2026-09-19 | Buffer Day - Catch-up / Rest / Light Review | Use this day to revisit any topic that still feels shaky, catch up on missed days, or rest fully if on track - both are valid uses of this day | Doc | Personal discretion | Flexible | Not Started | Medium | You have intentionally built slack into the plan - use it without guilt